## Points
Begin with first funding source and compute the remaining balance
Compare the Debt Commitment to the Accumulated Opening Balance
Difference is Remaining Commitment
Use the Remaining Commitment for MIN Test
Make Min Test
Next, Work through the Second

## Blank Exercise
Sources and Uses Summary
| Funding Assumptions |  |  |  | Int Rate
|  | Equity |  | 165.8037
|  | Senior Debt |  | 500 | 4%
|  | Sub Debt |  | 100 | 8%
|  |  | Total | 765.8037
Funding Analysis
|  | Period |  |  | -4 | -3 | -2 | -1 | 0
Funding Needs
|  | Construction Input |  | 720 | 65 | 185 | 180 | 220 | 70
Add: Interest on Sub-Debt
Add: Interest on Sr-Debt
Construction Input - Financing Needs
Equity Commitment
Amount already Contributed (opening balance)
Remaining Amount to Commit
Opening Balance
Amount Commited this Period - MIN
Closing Balance
Sub-total - Financing Needs After Equity
Sub-Debt Commitment
Amount Already Commited
Remaining Amount to Commit
Opening Balance
Amount Commited this Period - MIN
Closing Balance
Interest on Sub Debt
Sub-total - Financing Needs after Sub-Debt
Opening Balance
Amount Commited this Period
Closing Balance
Interest on Sub Debt

## Completed Exercise
Assumptions
| Funding Assumptions |  |  |  | Int Rate
|  | Equity |  | 165.8037 |  |  |  | Closing Balance |  | 500
|  | Senior Debt |  | 500 | 4% |  |  | Input |  | 500
|  | Sub Debt |  | 100 | 8% |  |  | Difference |  | 0
|  |  | Total | 765.8037
Funding
|  | Period |  |  | -4 | -3 | -2 | -1 | 0
Funding Needs
|  | Construction Input |  | 720 | 65 | 185 | 180 | 220 | 70
|  | Add: Interest on Sub-Debt |  |  | 0 | 0 | 6.7357 | 8 | 8
|  | Add: Interest on Sr-Debt |  |  | 0 | 0 | 0 | 6.8373 | 16.2308
|  | Construction Input - Financing Needs |  | 765.8037 | 65 | 185 | 186.7357 | 234.8373 | 94.2308
|  | Equity Commitment |  | 165.8037 | 165.8037 | 165.8037 | 165.8037 | 165.8037 | 165.8037
|  | Amount already Contributed (opening balance) |  |  | 0 | 65 | 165.8037 | 165.8037 | 165.8037
|  | Remaining Amount to Commit |  |  | 165.8037 | 100.8037 | 0 | 0 | 0
|  | Opening Balance |  |  | 0 | 65 | 165.8037 | 165.8037 | 165.8037
|  | Amount Commited this Period with MIN |  |  | 65 | 100.8037 | 0 | 0 | 0
|  | Closing Balance |  |  | 65 | 165.8037 | 165.8037 | 165.8037 | 165.8037
|  | Sub-total - Financing Needs After Equity |  |  | 0 | 84.1963 | 186.7357 | 234.8373 | 94.2308
|  | Sub-Debt Commitment |  | 100 | 100 | 100 | 100 | 100 | 100
|  | Amount Already Commited |  |  | 0 | 0 | 84.1963 | 100 | 100
|  | Remaining Amount to Commit |  |  | 100 | 100 | 15.8037 | 0 | 0
|  | Opening Balance |  |  | 0 | 0 | 84.1963 | 100 | 100
|  | Amount Commited this Period - Opening Balance |  |  | 0 | 84.1963 | 15.8037 | 0 | 0
|  | Closing Balance |  |  | 0 | 84.1963 | 100 | 100 | 100
|  | Interest on Sub Debt |  | 8% | 0 | 0 | 6.7357 | 8 | 8
|  | Sub-total - Financing Needs after Sub-Debt |  |  | 0 | 0 | 170.932 | 234.8373 | 94.2308
|  | Opening Balance |  |  | 0 | 0 | 0 | 170.932 | 405.7692
|  | Amount Commited this Period |  |  | 0 | 0 | 170.932 | 234.8373 | 94.2308
|  | Closing Balance |  |  | 0 | 0 | 170.932 | 405.7692 | 500
|  | Interest on Sub Debt |  | 4% | 0 | 0 | 0 | 6.8373 | 16.2308

## Comprehensive Example
Assumptions
Funding Assumptions
|  | Equity |  |  | 200
|  | Sr Debt |  |  | 400
|  | Sub Debt |  |  | 280
|  |  | Total |  | 880
| Funding Requirements |  |  |  | 880
| Difference |  |  |  | 0
Funding Cascade
|  | Period |  |  | -4 | -3 | -2 | -1 | 0
|  | End of Construction |  |  | FALSE | FALSE | FALSE | FALSE | TRUE
|  | Construction Input - Financing Needs |  |  | 100 | 130 | 180 | 220 | 250
|  | Accumulated |  |  | 100 | 230 | 410 | 630 | 880
|  | Equity Commitment |  |  | 200 | 200 | 200 | 200 | 200
|  | Equity Already Drawn |  |  | 0 | 100 | 200 | 200 | 200
|  | Remaing Equity to Draw |  |  | 200 | 100 | 0 | 0 | 0
|  | Opening Balance |  |  | 0 | 100 | 200 | 200 | 200
|  | Add: Draws using MIN function |  |  | 100 | 100 | 0 | 0 | 0
|  | Closing Balance |  |  | 100 | 200 | 200 | 200 | 200
|  | Remaing Required Funding |  |  | 0 | 30 | 180 | 220 | 250
|  | Sub Debt Commitment |  |  | 280 | 280 | 280 | 280 | 280
|  | Sub Debt Drawn |  |  | 0 | 0 | 30 | 210 | 280
|  | Remaing Sub Debt to Draw |  |  | 280 | 280 | 250 | 70 | 0
|  | Opening Balance |  |  | 0 | 0 | 30 | 210 | 280
|  | Add: Draws using MIN function |  |  | 0 | 30 | 180 | 70 | 0
|  | Closing Balance |  |  | 0 | 30 | 210 | 280 | 280
|  | Remaining Funding for Senior |  |  | 0 | 0 | 0 | 150 | 250
|  | Sr Debt Commitment |  |  | 400 | 400 | 400 | 400 | 400
|  | Sr Debt Drawn |  |  | 0 | 0 | 0 | 0 | 150
|  | Remaing Sr Debt to Draw |  |  | 400 | 400 | 400 | 400 | 250
|  | Opening Balance |  |  | 0 | 0 | 0 | 0 | 150
|  | Add: Draws |  |  | 0 | 0 | 0 | 150 | 250
|  | Closing Balance |  |  | 0 | 0 | 0 | 150 | 400
With Capitalised Interest and Fees
|  |  |  | Increment |  | Single | Date | Capatilise |  |  | Fee | Order | Target | Capitalise | Capitalise | Max Ratio
|  |  |  | Funding | Total | Funding | of | Interest | Fee | Base | Input | in Fund | DSCR | Interest | Fee | of Debt | Interest | Annuity
| Funding Assumptions |  |  | Tranche | Funding | Period | Funding | Portion | Portion | Funding | Percent | Cascade | Senior | Switch | Switch | to Cap | Rate | Repay
|  | Equity |  | FALSE | 50 | TRUE | 1 | 0 | 0 | 50 | 0% | 1 |  | FALSE | FALSE | 5% | 0% | FALSE
|  | Sub Debt |  | TRUE | 67.3344 | FALSE |  | 3.3667 | 3.3667 | 67.3344 | 1% | 3 |  | TRUE | TRUE | 85% | 5% | TRUE
|  | Senior Debt |  | FALSE | 600 | FALSE |  | 132.6656 | 30 | 762.6656 | 2% | 2 | 1.25 | TRUE | TRUE | 5% | 10% | FALSE
VAT Facility
[5 empty] | 717.3344 | 136.0323 | 33.3667 | 880
|  | Max Iterations |  | max_iter | 200
|  | Total Funding Computed |  | from | 880 | funding_from
|  | Total Funding Input |  | to | 880 | funding_input
|  | Difference |  | difference | 0 | funding_difference
|  | Sub Debt Computed (Balance) |  | from | 67.3344 | sub_debt_from
|  | Sub Debt Input |  | to | 67.3344 | sub_debt_to
|  | Difference |  | difference | 0 | sub_debt_difference
|  | Senior Base Funding Computed |  | from | 762.6656 | senior_from |  | 925.3312
|  | Senior Base Fixed |  | to | 762.6656 | senior_to
|  | Difference |  | difference | 0 | senior_difference
|  | Total Difference |  |  | 0 | total_difference
Funding Requirements
|  | Construction |  |  | 880
DSRA Pre-funding
|  | Interest Paid |  |  | 0
|  | Fees Paid |  |  | 0
|  | Total |  |  | 880
Funding Cascade
|  | Period |  |  | -4 | -3 | -2 | -1 | 0
|  | End of Construction |  |  | FALSE | FALSE | FALSE | FALSE | TRUE
|  | Construction Period |  |  | TRUE | TRUE | TRUE | TRUE | TRUE
Total Funding Requirement
|  | Construction |  |  | 100 | 130 | 180 | 220 | 250
|  | Add: Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Add: Fees Paid |  |  | 0 | 0 | 0 | 0 | 0
DSRA
|  | Total Cash Funding |  |  | 100 | 130 | 180 | 220 | 250
First Tranche
| 1 | 1 | Equity
|  | Total Commitment Incl Cap Int |  | 50 | 50 | 50 | 50 | 50 | 50
|  | Less: Total Capitalised Interest and Fees |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total to Use for Cash Funding |  | 50 | 50 | 50 | 50 | 50 | 50
|  | Less: Amount Already Drawn |  |  | 0 | 50 | 50 | 50 | 50
|  | Plus: Used for Fees and Cap Int |  |  | 0 | 0 | 0 | 0 | 0
|  | Remaining Amount to Draw |  |  | 50 | 0 | 0 | 0 | 0
Equity Balance
|  | Opening Balance |  |  | 0 | 50 | 50 | 50 | 50
|  | Add: Draws |  | 50 | 50 | 0 | 0 | 0 | 0
|  | Add: Cap Int |  |  | 0 | 0 | 0 | 0 | 0
|  | Add: Cap Fees |  |  | 0 | 0 | 0 | 0 | 0
|  | Closing Balance |  |  | 50 | 50 | 50 | 50 | 50
|  | Interest Rate |  | 0% | 0% | 0% | 0% | 0% | 0%
|  | Interest Accrued |  |  | 0 | 0 | 0 | 0 | 0
|  | Interest Capitalised |  | FALSE | 0 | 0 | 0 | 0 | 0
|  | Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Fee Percent |  | 0% | 0% | 0% | 0% | 0% | 0%
|  | Total Balance |  | 50 | 50 | 50 | 50 | 50 | 50
|  | Total Fees |  |  | 0 | 0 | 0 | 0 | 0
|  | Fees Capitalised |  | FALSE | 0 | 0 | 0 | 0 | 0
|  | Fees Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Accumulated Cap Int and Fee |  |  | 0 | 0 | 0 | 0 | 0
|  | Total Cap Interest |  | 0
|  | Total Cap Fees |  | 0
| Remaing Cash Required Funding After First Tranche |  |  |  | 50 | 130 | 180 | 220 | 250
Second Tranche
| 2 | 3 | Senior Debt
|  | Total Commitment |  | 600 | 600 | 600 | 600 | 600 | 600
|  | Less: Used for Cap Int and Fees |  | 168.3458 | 168.3458 | 168.3458 | 168.3458 | 168.3458 | 168.3458
|  | Total for Draws |  | 762.6656 | 762.6656 | 762.6656 | 762.6656 | 762.6656 | 762.6656
|  | Less: Amount Drawn (OB) |  |  | 0 | 56 | 197.6 | 403.36 | 669.696
|  | Plus: Used for Fees and Cap Int |  |  | 0 | 6 | 17.6 | 43.36 | 89.696
|  | Remaing Sub Debt to Draw |  |  | 762.6656 | 712.6656 | 582.6656 | 402.6656 | 182.6656
|  | Opening Balance |  |  | 0 | 56 | 197.6 | 403.36 | 669.696
|  | Add: Funding Outflows |  | 762.6656 | 50 | 130 | 180 | 220 | 182.6656
|  | Add: Captitalised Interest |  | 792.6656 | 0 | 5.6 | 19.76 | 40.336 | 66.9696
|  | Add: Capitalised Fees |  | 192.6656 | 6 | 6 | 6 | 6 | 6
|  | Closing Balance |  |  | 56 | 197.6 | 403.36 | 669.696 | 925.3312
|  | Interest Rate |  |  | 10% | 10% | 10% | 10% | 10%
|  | Interest Accrued |  |  | 0 | 5.6 | 19.76 | 40.336 | 66.9696
|  | Capitalised Interest |  | TRUE | 0 | 5.6 | 19.76 | 40.336 | 66.9696
|  | Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Accumulated Cap Interest |  |  | 0 | 5.6 | 25.36 | 65.696 | 132.6656
|  | Fee Percent |  | 2% | 1% | 1% | 1% | 1% | 1%
|  | Base for Fees |  | 600 | 600 | 600 | 600 | 600 | 600
|  | Total Fees |  |  | 6 | 6 | 6 | 6 | 6
|  | Fees Capitalised |  | TRUE | 6 | 6 | 6 | 6 | 6
|  | Fees Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Capitalised Interst and Fees |  |  | 6 | 17.6 | 43.36 | 89.696 | 162.6656
|  | Accumulated Fees |  |  | 6 | 12 | 18 | 24 | 30
|  | Total Interest Capitalsied |  | 132.6656
|  | Total Fees Capitalised |  | 30
|  | Total Capitalised |  | 162.6656
| Remaining Cash Requirements after Second Tranche |  |  |  | 0 | 0 | 0 | 0 | 67.3344
Third Tranche
| 3 | 2 | Sub Debt
|  | Total Commitment Incl Cap Int |  | 67.3344 | 67.3344 | 67.3344 | 67.3344 | 67.3344 | 67.3344
|  | Less: Total Capitalised Interest and Fees |  | 3.7207 | 3.7207 | 3.7207 | 3.7207 | 3.7207 | 3.7207
|  | Sub-total to Use for Cash Funding |  | 67.3344 | 67.3344 | 67.3344 | 67.3344 | 67.3344 | 67.3344
|  | Less: Amount Already Drawn |  |  | 0 | 0.67334 | 1.3804 | 2.1227 | 2.9022
|  | Plus: Used for Fees and Cap Int |  |  | 0 | 0.67334 | 1.3804 | 2.1227 | 2.9022
|  | Remaining Amount to Draw |  |  | 67.3344 | 67.3344 | 67.3344 | 67.3344 | 67.3344
Sub Debt Balance
|  | Opening Balance |  |  | 0 | 0.67334 | 1.3804 | 2.1227 | 2.9022
|  | Add: Draws |  | 67.3344 | 0 | 0 | 0 | 0 | 67.3344
|  | Add: Cap Int |  |  | 0 | 0.033667 | 0.069018 | 0.10614 | 0.14511 |  |  |  | Int = OB x Rate
|  | Add: Cap Fees |  |  | 0.67334 | 0.67334 | 0.67334 | 0.67334 | 0.67334 |  |  |  | OB = CB - Int - Draws - Fees
|  | Closing Balance |  |  | 0.67334 | 1.3804 | 2.1227 | 2.9022 | 71.0551 |  |  |  | Int = (CB - Int - Draws - Fees) x Rate
Int = (CB - Int - Draws - Fees) x Rate
|  | Interest Rate |  | 5% | 5% | 5% | 5% | 5% | 5% |  |  |  | Int + Int x Rate = (CB - Draws - Fees) x Rate
|  | Interest Accrued |  |  | 0 | 0.033667 | 0.069018 | 0.10614 | 0.14511 |  |  |  | Int x (1+Rate) = (CB - Draws - Fees) x Rate
|  | Interest Capitalised |  | TRUE | 0 | 0.033667 | 0.069018 | 0.10614 | 0.14511 |  |  |  | Int = (CB- Draws - Fees) x Rate/(1+Rate)
|  | Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Fee Percent |  | 1% | 1% | 1% | 1% | 1% | 1%
|  | Total Balance |  | 67.3344 | 67.3344 | 67.3344 | 67.3344 | 67.3344 | 67.3344
|  | Total Fees |  |  | 0.67334 | 0.67334 | 0.67334 | 0.67334 | 0.67334
|  | Fees Capitalised |  | TRUE | 0.67334 | 0.67334 | 0.67334 | 0.67334 | 0.67334
|  | Fees Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Accumulated Cap Int and Fee |  |  | 0.67334 | 1.3804 | 2.1227 | 2.9022 | 3.7207
|  | Total Cap Interest |  | 0.35393
|  | Total Cap Fees |  | 3.3667
Uses of Funds - Funding Requirements
|  | Construction |  |  | 100 | 130 | 180 | 220 | 250
|  | Interest During Construction |  |  | 0 | 5.6337 | 19.829 | 40.4421 | 67.1147
|  | Fees |  |  | 6.6733 | 6.6733 | 6.6733 | 6.6733 | 6.6733
Pre-funding of DSRA
|  |  | Total |  | 106.6733 | 142.307 | 206.5024 | 267.1155 | 323.7881
Sources of Funds
|  | Equity |  |  | 50 | 0 | 0 | 0 | 0
|  | Senior Debt |  |  | 50 | 130 | 180 | 220 | 182.6656
|  | Sub Debt |  |  | 0 | 0 | 0 | 0 | 67.3344
|  | Equity Capitalised Interest and Fees |  |  | 0 | 0 | 0 | 0 | 0
|  | Senior Debt Capitalised Interest and Fees |  |  | 6 | 11.6 | 25.76 | 46.336 | 72.9696
|  | Sub Debt Capitalised Interest and Fees |  |  | 0.67334 | 0.70701 | 0.74236 | 0.77948 | 0.81845
|  |  | Total |  | 106.6733 | 142.307 | 206.5024 | 267.1155 | 323.7881
With Capitalised Interest Only
|  |  |  | Increment |  | Capatilise |  |  | Fee | Order | Target | Capitalise | Capitalise | Max Ratio
|  |  |  | Funding | Total | Interest | Fee | Base | Input | in Fund | DSCR | Interest | Fee | of Debt | Interest | Annuity
| Funding Assumptions |  |  | Tranche | Funding | Portion | Portion | Funding | Percent | Cascade | Senior | Switch | Switch | to Cap | Rate | Repay
|  | Equity |  | FALSE | 50 | 0 |  | 50 |  | 1 |  | FALSE |  | 5% | 0% | FALSE
|  | Sub Debt |  | TRUE | 317.9653 | 78.6848 |  | 239.2847 |  | 2 |  | TRUE |  | 85% | 5% | TRUE
|  | Senior Debt |  | FALSE | 638.0697 | 47.3502 |  | 590.7153 |  | 3 | 1.3 | TRUE |  | 5% | 10% | FALSE
[5 empty] | 1006.035 | 126.035 |  | 880
|  | Max Iterations |  |  | 200 | mx_iter
|  | Senior Base Funding Computed |  |  | 590.7195 | sr_from
|  | Senior Base Fixed |  |  | 590.7153 | sr_to
|  | Difference |  |  | 0.0042094 | sr_diff
|  | Total Difference |  |  | 0 | tot_diff
Funding Requirements
|  | Construction |  |  | 880
DSRA Pre-funding
Interest Paid
|  | Total |  |  | 880
Funding Cascade
|  | Period |  |  | -4 | -3 | -2 | -1 | 0
|  | End of Construction |  |  | FALSE | FALSE | FALSE | FALSE | TRUE
|  | Construction Period |  |  | TRUE | TRUE | TRUE | TRUE | TRUE
Total Funding Requirement
|  | Construction |  |  | 100 | 130 | 180 | 220 | 250
|  | Add: Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
DSRA
|  | Total Cash Funding |  |  | 100 | 130 | 180 | 220 | 250
First Tranche
| 1 | 1 | Equity
|  | Total Commitment Incl Cap Int |  | 50 | 50 | 50 | 50 | 50 | 50
|  | Less: Total Capitalised Interest and Fees |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub-total to Use for Cash Funding |  | 50 | 50 | 50 | 50 | 50 | 50
|  | Less: Amount Already Drawn |  |  | 0 | 50 | 50 | 50 | 50
|  | Plus: Used for Fees and Cap Int |  |  | 0 | 0 | 0 | 0 | 0
|  | Remaining Amount to Draw |  |  | 50 | 0 | 0 | 0 | 0
Equity Balance
|  | Opening Balance |  |  | 0 | 50 | 50 | 50 | 50
|  | Add: Draws |  | 50 | 50 | 0 | 0 | 0 | 0
|  | Add: Cap Int |  |  | 0 | 0 | 0 | 0 | 0
|  | Closing Balance |  |  | 50 | 50 | 50 | 50 | 50
|  | Interest Rate |  | 0% | 0% | 0% | 0% | 0% | 0%
|  | Interest Accrued |  |  | 0 | 0 | 0 | 0 | 0
|  | Interest Capitalised |  | FALSE | 0 | 0 | 0 | 0 | 0
|  | Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Accumulated Cap Int and Fee |  |  | 0 | 0 | 0 | 0 | 0
|  | Total Cap Interest |  | 0
| Remaing Cash Required Funding After First Tranche |  |  |  | 50 | 130 | 180 | 220 | 250
Second Tranche
| 2 | 2 | Sub Debt
|  | Total Commitment |  | 317.9653 | 317.9653 | 317.9653 | 317.9653 | 317.9653 | 317.9653
|  | Less: Used for Cap Int and Fees |  | 168.3458 | 168.3458 | 168.3458 | 168.3458 | 168.3458 | 168.3458
|  | Total for Draws |  | 239.2847 | 239.2847 | 239.2847 | 239.2847 | 239.2847 | 239.2847
|  | Less: Amount Drawn (OB) |  |  | 0 | 50 | 185 | 262.7847 | 289.0632
|  | Plus: Used for Fees and Cap Int |  |  | 0 | 0 | 5 | 23.5 | 49.7785
|  | Remaing Sub Debt to Draw |  |  | 239.2847 | 189.2847 | 59.2847 | 0 | 0
|  | Opening Balance |  |  | 0 | 50 | 185 | 262.7847 | 289.0632
|  | Add: Funding Outflows |  | 239.2847 | 50 | 130 | 59.2847 | 0 | 0
|  | Add: Captitalised Interest |  | 239.2847 | 0 | 5 | 18.5 | 26.2785 | 28.9063
|  | Closing Balance |  |  | 50 | 185 | 262.7847 | 289.0632 | 317.9695
|  | Interest Rate |  |  | 10% | 10% | 10% | 10% | 10%
|  | Interest Accrued |  |  | 0 | 5 | 18.5 | 26.2785 | 28.9063
|  | Capitalised Interest |  | TRUE | 0 | 5 | 18.5 | 26.2785 | 28.9063
|  | Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Accumulated Cap Interest |  |  | 0 | 5 | 23.5 | 49.7785 | 78.6848
|  | Capitalised Interest and Fees |  |  | 0 | 5 | 23.5 | 49.7785 | 78.6848
|  | Total Interest Capitalsied |  | 78.6848
|  | Total Capitalised |  | 78.6848
| Remaining Cash Requirements after Second Tranche |  |  |  | 0 | 0 | 120.7153 | 220 | 250
Third Tranche
| 3 | 3 | Senior Debt
|  | Total Commitment Incl Cap Int |  | 638.0697 | 638.0697 | 638.0697 | 638.0697 | 638.0697 | 638.0697
|  | Less: Total Capitalised Interest and Fees |  | 47.3502 | 47.3502 | 47.3502 | 47.3502 | 47.3502 | 47.3502
|  | Sub-total to Use for Cash Funding |  | 590.7153 | 590.7153 | 590.7153 | 590.7153 | 590.7153 | 590.7153
|  | Less: Amount Already Drawn |  |  | 0 | 0 | 0 | 120.7153 | 352.7868
|  | Plus: Used for Fees and Cap Int |  |  | 0 | 0 | 0 | 0 | 12.0715
|  | Remaining Amount to Draw |  |  | 590.7153 | 590.7153 | 590.7153 | 470 | 250
Senior Debt Balance
|  | Opening Balance |  |  | 0 | 0 | 0 | 120.7153 | 352.7868
|  | Add: Draws |  | 590.7153 | 0 | 0 | 120.7153 | 220 | 250
|  | Add: Cap Int |  |  | 0 | 0 | 0 | 12.0715 | 35.2787
|  | Closing Balance |  |  | 0 | 0 | 120.7153 | 352.7868 | 638.0655
|  | Interest Rate |  | 10% | 10% | 10% | 10% | 10% | 10%
|  | Interest Accrued |  |  | 0 | 0 | 0 | 12.0715 | 35.2787
|  | Interest Capitalised |  | TRUE | 0 | 0 | 0 | 12.0715 | 35.2787
|  | Interest Paid |  |  | 0 | 0 | 0 | 0 | 0
|  | Accumulated Cap Int and Fee |  |  | 0 | 0 | 0 | 12.0715 | 47.3502
|  | Total Cap Interest |  | 47.3502
Uses of Funds - Funding Requirements
|  | Construction |  |  | 100 | 130 | 180 | 220 | 250
|  | Interest During Construction |  |  | 0 | 5 | 18.5 | 38.35 | 64.185
Pre-funding of DSRA
|  |  | Total |  | 100 | 135 | 198.5 | 258.35 | 314.185
Sources of Funds
|  | Equity |  |  | 50 | 0 | 0 | 0 | 0
|  | Sub Debt |  |  | 50 | 130 | 59.2847 | 0 | 0
|  | Senior Debt |  |  | 0 | 0 | 120.7153 | 220 | 250
|  | Equity Capitalised Interest and Fees |  |  | 0 | 0 | 0 | 0 | 0
|  | Sub Debt Capitalised Interest and Fees |  |  | 0 | 5 | 18.5 | 26.2785 | 28.9063
|  | Senior Debt Capitalised Interest and Fees |  |  | 0 | 0 | 0 | 12.0715 | 35.2787
|  |  | Total |  | 100 | 135 | 198.5 | 258.35 | 314.185
|  | EBITDA | [7 empty] | 130 | 133.9 | 137.917 | 142.0545 | 146.3161 | 150.7056 | 155.2268 | 159.8836 | 164.6801
|  | DSCR | [7 empty] | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
|  | Required Debt Service | [7 empty] | 100 | 103 | 106.09 | 109.2727 | 112.5509 | 115.9274 | 119.4052 | 122.9874 | 126.677
|  | Interest Rate | [7 empty] | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
|  | NPV |  | 638.0697
Debt Balance
|  |  | Opening Balance | [6 empty] | 638.0697 | 601.8767 | 559.0644 | 508.8808 | 450.4962 | 382.9949 | 305.367 | 216.4985 | 115.1609
|  |  | Less: Repayments | [6 empty] | 36.193 | 42.8123 | 50.1836 | 58.3846 | 67.5013 | 77.6279 | 88.8685 | 101.3375 | 115.1609
|  |  | Closing Balance | [5 empty] | 638.0697 | 601.8767 | 559.0644 | 508.8808 | 450.4962 | 382.9949 | 305.367 | 216.4985 | 115.1609 | -8.3844e-13
|  |  | Interest Expense | [6 empty] | 63.807 | 60.1877 | 55.9064 | 50.8881 | 45.0496 | 38.2995 | 30.5367 | 21.6498 | 11.5161
Comment
Copy and Past Macro
Button 621
Note on A1: Monica Lewinski: This demonstrates how to develop a cash flow waterfall for draw downs in the sources and uses of funds analysis. The first part is very simple and the next parts introduce complications that create an unresolvable circular reference The general approach is the same as with the cash flow waterfall in the cash flow statement which involves: - Setting up accont balances that show the remaining amount to draw - Using a lot of sub-total accounts - Usning the MIN Function The second part adds capitalised interest and fees which make the problem much more difficult.
Note on A51: Monica Lewinski: The general approach is to find one incremental tranche of funding. If the total funding needs including capitalised interest and fees are known, and if there is only one tranche to compute, the alternative funding can be computed.
Note on A217: Monica Lewinski: The general approach is to find one incremental tranche of funding. If the total funding needs including capitalised interest and fees are known, and if there is only one tranche to compute, the alternative funding can be computed.